## Information
Hazard and Risk Register Template
What is a Hazard and Risk Register Register?
A Hazard and Risk Register is a list of all the identified hazards, including the risk level and the controls implemented to eliminate or minimise the risks associated with the hazard.
The Hazard and Risk Register should provide an overview of the following:
• Date the hazard was reported;
• Location of the hazard;
• A brief description of the hazard;
• What controls are currently in place;
• The inherent risk ranking; (risk ranking with current controls only)
• Any additional controls identified;
• Hierarchy of control to be used;
• The residual risk ranking; (risk ranking with additional controls implemented)
• The person responsible for implementing the control/s;
• Due date for the control/s to be implemented;
• The date of completion; and
• The date due for the review of implemented controls.
The South Australian Mining and Quarrying Occupational Health and Safety Committee
Promoting Work Health and Safety in the Workplace
This workplace industry safety resource is developed and fully funded by the Mining and Quarrying Occupational Health and Safety Committee (MAQOHSC).
Disclaimer
IMPORTANT: The information in this guide is of a general nature, and should not be relied upon as individual professional advice. If necessary, legal advice should be obtained from a legal practitioner with expertise in the field of Work Health and Safety law (SA).
Although every effort has been made to ensure that the information in this guide is complete, current and accurate, the Mining and Quarrying Occupational Health and Safety Committee, any agent, author, contributor or the South Australian Government, does not guarantee that it is so, and the Committee accepts no responsibility for any loss, damage or personal injury that may result from the use of any material which is not complete, current and accurate.
Users should always verify historical material by making and relying upon their own separate inquiries prior to making any important decisions or taking any action on the basis of this information.
Creative Commons
This work is licenced under
Creative Commons Attribution – Non Commercial 4.0 International Licence.
The licence is available to view at http://creativecommons.org/licenses/by-nc/4.0/
This creative commons licence allows you to copy, communicate and or adapt our work for non-commercial purposes only, as long as you attribute the work to Mining and Quarrying Occupational Health and Safety Committee and abide by all the other licence terms therein.
ISBN 978-1-925361-72-8
Contact Information
Mining and Quarrying Occupational Health and Safety Committee (MAQOHSC)
Level 2, Torrens Building
220 Victoria Square
Adelaide SA 5000
Phone: (08) 8204 9842
Email: maqohsc@sa.gov.au
Website: www.maqohsc.sa.gov.au
2020-02-01

## Hazard & Risk Register Template
(Insert Company Name) Hazard and Risk Register Template | [13 empty] | Low | Moderate | High | Critical
Item | Date | Location | Description | Exisiting Controls | Inherent Risk Ranking | Additional Controls to be implemented | Hierarchy Of Control (select highest control) | Residual Risk Ranking | Responsible person | Due Date | Date Completed | Review Date | Comments | Elimination | Substitution | Isolation | Engineering | Adminstrative | PPE
1 | 2017-02-01 | Quarry | Excessive dust being produced from crusher discharge | Workers supplied Personal Protective Equipment (dust masks) | Critical | 1. Water system with misting sprays to be fitted to all discharge conveyors. 2. Fit testing of respirators to be conducted. 3. Dust Monitoring to be conducted. 4. Review of current Personal Protective Equipment to be conducted. | Engineering | Moderate | J.Bloggs | 2017-04-01 | 2017-04-04 | 2017-06-30

## Risk Matrix
Risk Matrix
Rating | Safety | Health | Environment | Equipment and Assets | Business Continuity | Community and Reputation | Liability
1 Minor | Single minor injury to one person. First aid or no treatment required. No lost time. | Reversible health effects of minor concern requiring first aid treatment at most. | Issues of non-continuous nature with promptly reversible impact or consequence (e.g. within shift). Low-level incident, site contained. | Below $5,000 (or 0.1% of operational budget based at $50,000,000). | Loss of operations for > ½ day. Reduction in capacity, < 10% for up to one month. | Unsubstantiated, low profile or no media attention. One-off complaint which is resolved via existing procedures. | Below $50,000 (or 0.1% of operational budget based at 50,000,000). Financial or accounting issue with ability to resolve with existing resources.
2 Moderate | Medically treated injury. Reversible injury. Requires treatment but does not lead to restricted duties. | Reversible health effects of concern that result in medical treatment but not restricted duties. | Issues of a non-continuous nature and minor impact and consequence. Low-level incident, site contained. Short term reversible (e.g. within days). | Between $5,000- $50,000 (or 0.1%- 0.5% of operational budget). | Loss of operations for > ½ day. Reduction in capacity, < per 20% for up to one month. Minor disruption to supply of services or technical support. | Substantiated, low impact, low media profile. Unresolved, low level community dissatisfaction, Repeated community complaints. | Between $50,000 - $100,000 (or 0.1% - 0.5% of operational budget). Financial or accounting issue requiring CFO resolution.
3 Serious | Reversible injury or moderate irreversible impairment. Less than 10 days lost time. | Severe but reversible health effects. Results in a lost time illness of less than 10 days. | Issues of a continuous nature - limited impact and consequence. Incident resulting in some site contamination. Medium term recovery impact. | Between $50,000 - $200,000 (or 0.5% - 3.5% of operational budget). Threat to property by known extreme organisations. | Loss of operations for one day to one week Reduction in capacity, < 30% for up to one month. Increased government interest. | Substantiated, public embarrassment, moderate media profile (front page, one day). Repeated community complaint. Community demonstration. Impact on share price. | Between $100,000 - $250,000 (or 0.5% - 3.5% of operational budget).
4 Major | Severe irreversible damage to one or more persons. Lost Time Injury greater than 10 days. | Severe and irreversible health effects or disabling illness. | Compliance issue with large fine, media attention. Serious harm not immediately recovered. Significant site contamination or off-site impact. Long term recovery. | Between $200,000 -$500,000 (or 3.5 -10% of operational budget). Confirmed threats, without actions. | Loss of operations for one week to one month. Reduction in capacity, < 50% for up to one month. Regulatory enquiry. | Substantiated, public embarrassment, high impact, major media attention. Local or state media interest. Severe community dissent. Criticism from NGO and / or government. | Between $250,000 - $1,000,000 (or 3.5 - 10% of operational budget). Financial or accounting issue requiring General Manager finance resolution.
5 Catastrophic | Single fatality. Permanent disabling injuries. | Life threatening or permanently disabling illness. | Issues of a continuous nature with major long-term impact and potentially serious consequences. | Above $1,000,000 (or more than 10% of operational budget). Escalating threats or actions. | Loss of operations for > 1-3 months. Loss of permit to operate. Total loss of production for more than one month. | Substantiated, public embarrassment, multiple impacts, long lasting widespread media coverage. Severe, prolonged community dissent. | Above $1,000,000 (or more than 10% of operational budget).
Consequence
|  | 1 | 2 | 3 | 4 | 5
|  | Minor | Moderate | Serious | Major | Catastrophic
Likelihood | A | 10 | 16 | 20 | 23 | 25
Almost Certain
| B | 7 | 12 | 17 | 21 | 24
Likely
| C | 4 | 8 | 13 | 19 | 22
Possible
| D | 2 | 5 | 9 | 14 | 18
Unlikely
| E | 1 | 3 | 6 | 11 | 15
Rare
Risk result | Rating | Definition | Level of involvement | Rating | Descriptor | Description | Suggested frequency
Note: When a potential consequence is classified as catastrophic, immediate and on-going intervention is required from the CEO to ensure control measures are adequate. |  |  |  | A | Almost certain | The event is expected to occur | Recurring event during the lifetime of a projec t /operation, e.g. More than once per month
19 - 25 | Critical | Imperative to eliminate or reduce risk to a lower level by the introduction of controls. Formal risk assessment required. | CEO needs to review. | B | Likely | The event will probably occur | Event that may occur frequently during the lifetime of a project / operation, e.g. At least once per year
2013-11-18 | High | Corrective action required. | General Manager or Department Manager review required. | C | Possible | The event should occur | Event that may occur during the lifetime of a project / operation e.g. once in 3 years
|  | Normally permits required to perform work. Safe Work Procedure or Job Hazard Analysis mandatory. |  | D | Unlikely | The event could occur | Event that is unlikely to occur during the lifetime of a project / operation e.g. once in 10 years
2013-06-10 | Moderate | Corrective action required. Job Hazard Analysis or Safe Work Procedure required. | Supervisor review required. | E | Rare | The event may occur only in exceptional circumstances | Event that is very unlikely to occur during the lifetime of a project / operation, e.g. Once in 15 years
2013-01-05 | Low | Corrective action where practical. | Manage by routine procedures at operational level.
Take 5 risk assessment required.